## How to use
AI gap patterns — decision register
How to use this tracker
Purpose | Each row is a policy / governance / product-logic decision that must be settled before the matching UI can be designed. Companion context: proposals/2026-07-20-ai-gap-policy-decisions.md.
What to fill | Only the yellow columns: Decision, Owner sign-off, Status, Notes. Leave the reference columns (A–H) as-is.
Suggested DRI | Who should MAKE the call (primary owner). 'Consulted' = functions that must be heard before it's final.
Depends on | Decisions that must be resolved first; don't finalize a row until its dependencies are Decided.
Status values | Open · In discussion · Decided · Parked (not now).
Filter tip | Filter the register by 'Suggested DRI' to find your rows.
DRI legend
PM | Product Management (owns the call unless noted)
DES | Design
LEG | Legal & Privacy
SEC | Security / IT admin
CMP | Compliance
ML | Data / ML Platform
ENG | Engineering
FIN | Finance / Billing
BRD | Brand / Content

## Decision register
ID | Area | Decision to make | Why it blocks UI | Options / considerations | Suggested DRI | Consulted | Depends on | Decision | Owner sign-off | Status | Notes
M0 | (example) | <the call to make> | <what UI is blocked> | <option A · option B> | PM | LEG |  | e.g. Opt-in for enterprise, opt-out for free | J. Cho | In discussion | Revisit after legal review
M1 | Memory | What is eligible to be remembered? | Can't design a memory manager until the content class is defined | Preferences/identity · explicit user facts · derived behavior · raw conversation | PM | LEG, SEC
M2 | Memory | Scope & isolation model | Determines the whole memory IA and isolation guarantees | Per-user global · per-workspace · per-space · per-agent; define leak boundaries | PM | SEC
M3 | Memory | Capture trigger: auto / explicit / hybrid | Decides whether a 'saved to memory' affordance exists at all | Automatic · explicit confirm · hybrid | PM | DES
M4 | Memory | Retention, expiry & deletion rights | Governs delete/purge controls and any expiry UI | Indefinite · decay · expiry; user-deletable; admin purge | LEG | PM, SEC
M5 | Memory | Visibility & edit rights | Sets who sees/edits which memories in the UI | User view/edit all · admin visibility of workspace memory | PM | SEC, LEG
M6 | Memory | Enterprise admin controls | Defines the admin-console scope for memory | Org disable · retention policy · audit access | SEC | CMP, PM
M7 | Memory | Is memory used for training? | Honesty of memory disclosure copy depends on this | Runtime recall only · also training (opt-in) | LEG | ML | D1, D3
I1 | Incognito | Granularity of memory-off | Determines the control surface | Session toggle · per-message · no-memory space | PM | DES
I2 | Incognito | What incognito excludes | Defines what the mode truthfully promises; audit may forbid true off-record | Memory only · + training · + logging (may conflict w/ compliance) | CMP | LEG, SEC
I3 | Incognito | Connector behavior in incognito | Which integrations disable / go read-only | Disable all · read-only · unaffected | SEC | PM
I4 | Incognito | Admin authority over incognito | Whether orgs can forbid or force it | Org can forbid · can force · user choice | CMP | PM
D1 | Data ownership | Training default (opt-in/opt-out, by tier) | Gates the whole data-controls UI and Memory M7 | Opt-in · opt-out · differs by tier | LEG | PM, exec, ML
D2 | Data ownership | Retention default & duration | Drives retention settings + copy | Fixed duration · configurable range | LEG | SEC
D3 | Data ownership | Separate training vs retention permissions | Determines one toggle or two | Independent controls · combined | LEG | PM
D4 | Data ownership | Scope of control (user/workspace/admin) | Sets where the controls live | User · workspace · org-admin only | SEC | PM
D5 | Data ownership | Residency, deletion, export obligations | Compliance features (GDPR etc.) | Region residency · right-to-delete · export | CMP | LEG, ENG
D6 | Data ownership | Connector-sourced data governance | Retention/training + prompt-injection treatment of pulled data | Retain/train rules · treat as untrusted | SEC | LEG
D7 | Data ownership | In-product disclosure of defaults | Where the default is stated in the UI itself | Settings copy · onboarding · inline | DES | LEG
C1 | Consent | Do we capture third-party data at all? | GATE — everything else in Consent parks if 'no' | Yes · No (park section) | PM
C2 | Consent | Consent model (opt-in, per-purpose, reversible) | Shapes the consent flow | Opt-in · per-purpose split · reversible | LEG | PM | C1
C3 | Consent | Multi-party notification | How non-users in a session are notified | In-session indicator · pre-join notice | LEG | DES | C1
C4 | Consent | Jurisdictional consent laws | Regional handling of recording | One-party · two-party regions | CMP | LEG | C1
A1 | Action plan | Trigger threshold for requiring a plan | Defines when the plan UI appears at all | Compute cost · blast radius · irreversibility · external effects | PM | ENG, SEC
A2 | Action plan | Advisory vs contractual | Which task classes block vs merely show | Show-only · block-until-approved by class | PM | SEC
A3 | Action plan | Editability & plan/execution fidelity | Whether plan is editable + divergence handling | Editable · read-only; must-match vs explain-divergence | PM | ENG
A4 | Action plan | Bypass / trust settings | Whether gating can be disabled | Per-user · per-org · per-agent default | PM
A5 | Action plan | Overlap with ProposalCard | Avoid double-confirmation; governs the relationship | Plan superset of proposals · separate gate | DES | PM
E1 | Cost estimates | Unit & currency exposed | Determines what the estimate shows | Tokens · credits · money mapping | FIN | PM
E2 | Cost estimates | Estimation method, range & accuracy stance | Confidence display + liability if actual exceeds | Point · low-high range; over-run stance | ML | FIN
E3 | Cost estimates | When to show (always vs threshold) | Placement / trigger logic | Always · above a cost threshold | PM
E4 | Cost estimates | Informational vs enforcing | Whether it blocks/queues; ties to usage meter | Info-only · block/queue at limit | PM | FIN
E5 | Cost estimates | Cost-driver detail exposed | How much breakdown to show | Total only · itemized drivers | DES | ENG
B1 | Branches | Persistence & audit representation | How branches appear in history / audit trail | Saved · ephemeral; audit-trail form | PM | ENG
B2 | Branches | Context inheritance into a branch | Default carried context + user control | Inherit all · selectable (memory/files/model) | PM | DES
B3 | Branches | Merge / adopt semantics | How a branch is adopted back + what it records | Adopt answer · promote variant | DES | PM
V1 | Variations | Variation cost governance | N variations multiply compute | Cap count · count vs quota · surface via estimate | PM | FIN
VT1 | Voice & tone | Ownership & scope of brand voices | Who creates/edits; where stored | Org · team · personal | BRD | PM
VT2 | Voice & tone | Enforcement (default/constraint/suggestion) | How strongly applied + override rules | Default · hard constraint · suggestion | BRD | PM
VT3 | Voice & tone | Voice vs agent personality separation | Prevents brand voice and personality fighting | Distinct layers · merged | BRD | DES
VT4 | Voice & tone | Review/approval of custom voices | Governance of team-authored voices | Reviewed · open | BRD
MO1 | Modes | Mode taxonomy (closed set?) | Defines the mode switcher and its governance | Closed governed set · open | PM | DES
MO2 | Modes | Inheritance / reset across modes | What carries vs resets on switch | Carry context · reset per mode | PM | DES
MO3 | Modes | Per-mode permissions & cost + org lock | Whether modes differ + can be locked | Uniform · differ; org-lockable | PM | SEC
N1 | Nudges | Nudge content policy (anti growth-theater) | What a nudge may promote | Capability only · premium-upsell rules | PM | BRD
PD1 | Prompt details | What prompt/config is safe to expose & copy | Prevents leaking system prompt / secrets | Full · redacted · none | SEC | PM